## Test plan
Test plan
Project name: |  | Shopify partners store
Project description: |  | The Shopify Partners account will allow us to create as many development stores as we need for free
Module name: |  | https://learn.cypress.io/tutorials/creating-a-shopify-partners-store
Date: |  | 2023-03-21
MODULE | No. | TEST CASE | STEP | STEP DESCRIPTION | STATUS | EXPECTED RESULT | ACTUAL RESULT
Home Screen | 1 | H-001 Correctness of URL and title and cookies acceptance |  | Check if the URL and title contain correct data
|  |  | 1 | Launch browser | Passed | Browser successfully launched | As expected
|  |  | 2 | Open http://localhost:3000/ | Passed | URL should contain localhost:3000 and title ACME Storefront | As expected
|  |  | 3 | Check if cookies banner is not visible | Passed | Cookies banner is not visible (cookies are accepted before each test case) | As expected
Home Screen | 2 | H-002 Grid products count and effect |  | Check if each of the grids contain 3 products and check image hover effect
|  |  | 1 | Launch browser | Passed | Browser successfully launched | As expected
|  |  | 2 | Open http://localhost:3000/ | Passed | Page successfully opened, upper grid should contain 3 products | As expected
|  |  | 3 | Move mouse to each of the images in upper grid | Passed | Hover effect is working properly | As expected
|  |  | 4 | Scroll down to lower product grid | Passed | Lower product grid is visible and contains 3 products | As expected
|  |  | 5 | Move mouse to each of the images in upper grid | Passed | Hover effect is working properly | As expected
Home Screen | 3 | H-003 Sliders products count |  | Check if upper slider contains 3 products and lower slider 1 product
|  |  | 1 | Launch browser | Passed | Browser successfully launched | As expected
|  |  | 2 | Open http://localhost:3000/ | Passed | Page successfully opened | As expected
|  |  | 3 | Scroll down to see the upper slider | Passed | Upper slider is visible and contains 3 products with correct names | As expected
|  |  | 4 | Scroll down to see the lower slider | Passed | Lower slider is visible and contains 1 product with correct name | As expected
Home Screen | 4 | H-004 Shopify information header and content |  | Check if shopify info part contains correct header and content
|  |  | 1 | Launch browser | Passed | Browser successfully launched | As expected
|  |  | 2 | Open http://localhost:3000/ | Passed | Page successfully opened | As expected
|  |  | 3 | Scroll down to see information part about Shopify | Passed | Information part is visible with correct header and content | As expected
|  |  | 4 | Click on Read it here button | Passed | User is redirected to shopify.vercel.store website | As expected
Home Screen | 5 | H-005 Link redirections in footer |  | Check links in footer redirect user to correct pages
|  |  | 1 | Launch browser | Passed | Browser successfully launched | As expected
|  |  | 2 | Open http://localhost:3000/ | Passed | Page successfully opened | As expected
|  |  | 3 | Scroll down to the footer | Passed | Footer is visible | As expected
|  |  | 4 | Click on Home button | Passed | User is redirected to shopify.vercel.store website | As expected
|  |  | 5 | Go back to page | Passed | Localhost is displayed | As expected
|  |  | 6 | Click on Contact button | Passed | User is redirected to vercel.com/contact website | As expected
|  |  | 7 | Go back to page | Passed | Localhost is displayed | As expected
|  |  | 8 | Click on GitHub logo | Passed | User is redirected to Vercel GitHub website | As expected
Home Screen | 6 | H-006 Change website background |  | Check if background changing function is working correctly
|  |  | 1 | Launch browser | Passed | Browser successfully launched | As expected
|  |  | 2 | Open http://localhost:3000/ | Passed | Page successfully opened | As expected
|  |  | 3 | Scroll down to the footer | Passed | Footer is visible | As expected
|  |  | 4 | Change website background to Light | Passed | Background successfully changed to White | As expected
|  |  | 5 | Change website background to System | Passed | Background successfully changed to Black | As expected
|  |  | 6 | Change website background to Dark | Passed | Background successfully changed to Black | As expected
Home Screen | 7 | H-007 Change website language |  | Check if is possible to change the language of website
|  |  | 1 | Launch browser | In work | Browser successfully launched
|  |  | 2 | Open http://localhost:3000/ | In work | Page successfully opened
|  |  | 3 | Scroll down to the footer | In work | Footer is visible
|  |  | 4 | Change website language to Espanyol | In work | Website language successfully changed to Espanyol
|  |  | 5 | Change website language to English | In work | Website language successfully changed to English
Home Screen | 8 | H-008 Show all products and order them |  | Show all products by clicking on button All and order them
|  |  | 1 | Launch browser | In work | Browser successfully launched
|  |  | 2 | Open http://localhost:3000/ | In work | Page successfully opened
|  |  | 3 | Click on All button in header | In work | Url should contain word search, page should contain 4 products with correct names
|  |  | 4 | Order products by option Price: Low to High | In work | Product prices should be ordered ascending
|  |  | 5 | Order products by option Price: High to Low | In work | Product prices should be ordered descending
|  |  | 6 | Click on Home page button in header | In work | Page should contain 2 products with correct names
Home Screen | 9 | H-009 Search for product |  | Search for product which is in offer and also for products not in offer
|  |  | 1 | Launch browser | In work | Browser successfully launched
|  |  | 2 | Open http://localhost:3000/ | In work | Page successfully opened
|  |  | 4 | Type Nike to search bar | In work | Search bar contains word Nike
|  |  | 5 | Check founded product (label and product count) | In work | Search page contains 1 product with Nike inside his name
|  |  | 6 | Go back to home page | In work | Localhost is displayed
|  |  | 7 | Clear search bar | In work | Search bar is empty
|  |  | 8 | Type Test to search bar | In work | Search bar contains word Test
|  |  | 9 | Check that no products are found | In work | Search page does not contain any found products
Home Screen | 10 | H-010 Add product to wishlist |  | Add product to wishlist before logging in and also after logging in
|  |  | 1 | Launch browser | In work | Browser successfully launched
|  |  | 2 | Open http://localhost:3000/ | In work | Page successfully opened
|  |  | 3 | Click on "heart" icon on product card | In work | Pop up for log in should appear
|  |  | 5 | Log in | In work | User successfully logged in
|  |  | 6 | Click on "heart" icon on product card again | In work | Pop up for log in should not appear
|  |  | 7 | Click on WishList icon in header | In work | Wishlist should be empty
Product Screen | 1 | P-001 Product actions with color options |  | Open product and check actions which can be performed on product
|  |  | 1 | Launch browser | In work | Browser successfully launched
|  |  | 2 | Open http://localhost:3000/ | In work | Page successfully opened
|  |  | 3 | Open first product in upper grid | In work | Product page successfully opened, product name is correct and also URL is correct
|  |  | 4 | Try every possible actions on product page | In work | Every color should be clickable and is possible to add it to cart
|  |  | 5 | Click on "heart" icon on product card | In work | Pop up for log in should appear
|  |  | 6 | Log in | In work | User successfully logged in
|  |  | 7 | Click on "heart" icon on product card again | In work | Pop up for log in should not appear
|  |  | 8 | Try additional info actions on product page | In work | In "empty" state Care and Details content should not be visible
|  |  | 9 | Click on Care button | In work | Collapsed content should be visible
|  |  | 10 | Click on Details button | In work | Collapsed content should be visible
Product Screen | 2 | P-002 Product actions with sizes options |  | Open product and check actions which can be performed on product
|  |  | 1 | Launch browser | In work | Browser successfully launched
|  |  | 2 | Open http://localhost:3000/ | In work | Page successfully opened
|  |  | 3 | Open second product in upper grid | In work | Product page successfully opened, product name is correct and also URL is correct
|  |  | 4 | Try every possible actions on product page | In work | Last size is not possible to add to cart
|  |  | 5 | Try additional info actions on product page | In work | In "empty" state Care and Details content should not be visible
|  |  | 6 | Click on Care button | In work | Collapsed content should be visible
|  |  | 7 | Click on Details button | In work | Collapsed content should be visible
Product Screen | 3 | P-003 Product page with request info |  | Open product and compare info from website with info from response
|  |  | 1 | Launch browser | In work | Browser successfully launched
|  |  | 2 | Open http://localhost:3000/ | In work | Page successfully opened
|  |  | 3 | Open second product in upper grid | In work | Product page successfully opened
|  |  | 4 | Send request to obtain product info | In work | Response of the request contains correct info which is also displayed in the product page like: product title, response length is 1, status of the product is active, variant of the product is size and has length 3, sizes in the webpage are the same as from the response, url contains info from response

## Possible results
Open
Passed
Failed
In work
Pridat produkt do kosika, sidebar sa zobrazi, skontrolovat meno atd, zmenit pocet, odstranit produkt z kosika
Nakup E2E test
Login testy
Registracia testy
Prihlaseny uzivatel menu testy